# CALQIC Roadmap

This roadmap is intended to support teams in clearly defining the opportunity and importance of their project, their aims and sub-aims, as well as key activities to support meeting their aims. This roadmap can also be used to build consensus, understanding, and support the project, and to have a single, brief and descriptive document to share broadly across the organization when it is helpful.

# Date Created: 						                      Date Last Modified:

| Organization: |  |
| --- | --- |
| Project Leads: |  |
| Project Team Members (Roles): |  |
| Decision Making Process: |  |
| What are we trying to accomplish? |  |
| Opportunity for Change: Background and Reason for Effort (In the teams’ own words, what’s your “why”? What problem (s) are you trying to solve?) |  |
| Aim Statement (What’s your overall goal and by when? Remember SMARTIE = Specific, Measurable, Ambitious, Relevant, Timebound, Inclusive, and Equitable) |  |

| Key Changes/Activities to support Sub-Aim: These are ideas for changes and activities that come out of brainstorms, driver diagrams, etc. | Measures for Sub-Aim: how will you know the change or activity you’re doing is working? |  |  |  |
| --- | --- | --- | --- | --- |
|  | Measures | Data Gathering Plan | Baseline | Goal |
| 1. We will train and attest 100% of our eligible clinicians through ACES Aware by October 31, 2020 |  |  |  |  |
| - Hold a focus group with clinicians from all three sites to understand facilitators and barriers to getting certified, and to screening for ACEs by January, 2021. - Develop training strategy based on feedback from the focus group by February 2021. - Test training strategy by March 2021. - Refine, and implement training strategy beginning April, 2021. | # of clinicians that completed the ACEs Aware training | Self reported: Roberto will collect data monthly by asking for an update at monthly all clinician meetings until all clinicians have been certified. | 0 | 20 |
| 2. All participating sites will be screening for ACEs by October 31, 2021 using PEARLS for pediatrics and/or an appropriate tool for adults. |  |  |  |  |
| 3. We will be able to report screening data by participating sites by October 31, 2021. |  |  |  |  |
| 4. We will be able to report screening data by race/ethnicity by October 31, 2021. |  |  |  |  |
| 5. We will screen at least 50% of the patients in our target/eligible population by October 31, 2021. |  |  |  |  |
| 6. Develop your own additional sub-aim(s) to address relational health and equity. |  |  |  |  |

| Existing Strengths | Opportunities for Change |
| --- | --- |
| Foundation |  |
| Environment |  |
| Education |  |
| Screening |  |
| Response |  |