# CALQIC Roadmap

This roadmap is intended to support teams in clearly defining the opportunity and importance of their project, their aims and sub-aims, as well as key activities to support meeting their aims. This roadmap can also be used to build consensus, understanding, and support the project, and to have a single, brief and descriptive document to share broadly across the organization when it is helpful.

#  Date Created: Date Last Modified:

|  |  |
| --- | --- |
| **Organization:** |  |
| **Project Leads:**  |  |
| **Project Team Members (Roles):** |  |
| **Decision Making Process:** |  |
| ***What are we trying to accomplish?*** |
| **Opportunity for Change: Background and Reason for Effort****(In the teams’ own words, what’s your “why”? What problem (s) are you trying to solve?)** |
|  |
| **Aim Statement** **(What’s your overall goal and by when? Remember SMARTIE = Specific, Measurable, Ambitious, Relevant, Timebound, Inclusive, and Equitable)**  |
|  |

|  |  |
| --- | --- |
| **Key Changes/Activities to support Sub-Aim:** These are ideas for changes and activities that come out of brainstorms, driver diagrams, etc.  | **Measures for Sub-Aim:** how will you know the change or activity you’re doing is working?  |
| ***Measures***  | ***Data Gathering Plan*** | ***Baseline*** | ***Goal*** |
| **1. We will train and attest 100% of our eligible clinicians through ACES Aware by October 31, 2020** |
| * Hold a focus group with clinicians from all three sites to understand facilitators and barriers to getting certified, and to screening for ACEs by January, 2021.
* Develop training strategy based on feedback from the focus group by February 2021.
* Test training strategy by March 2021.
* Refine, and implement training strategy beginning April, 2021.
 | # of clinicians that completed the ACEs Aware training  | Self reported: Roberto will collect data monthly by asking for an update at monthly all clinician meetings until all clinicians have been certified.  | 0 | 20  |
| **2. All participating sites will be screening for ACEs by October 31, 2021 using PEARLS for pediatrics and/or an appropriate tool for adults.**  |
|  |  |  |  |  |
| **3. We will be able to report screening data by participating sites by October 31, 2021.**  |
|  |  |  |  |  |
| **4. We will be able to report screening data by race/ethnicity by October 31, 2021.**  |
|  |  |  |  |  |
| **5. We will screen at least 50% of the patients in our target/eligible population by October 31, 2021.** |
|  |  |  |  |  |
| 6. **Develop your own additional sub-aim(s) to address relational health and equity.** |
|  |  |  |  |  |

|  |  |
| --- | --- |
| ***Existing Strengths***  | ***Opportunities for Change*** |
| **Foundation** |  |
|  |  |
| **Environment**  |  |
|  |  |
| **Education** |  |
|  |  |
| **Screening**  |  |
|  |  |
| **Response** |  |
|  |  |