## Sheet 1
SDOH Training and Communications Timeline 2019
[5 empty] | September |  |  |  | October |  |  |  |  | November |  |  |  |  | December
Task | Task/Method | Lead | Due | Status | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 19 | 1 | 2 | 3 | 4 | 5
1. Presentations to Leadership
a. Clin-Ops- why/plans/ask 2020 implementation and send pre-survey | Power Point | Beth | 2019-09-23 | ® | bar: September 3 to September 4
c. Board of Directors Quality Review Committee- why/plans/ask 2020 implementation | Power Point | Beth | 2019-11-14 | ± | bar: November 1 to November 3
d. Clin-Ops-pilot outcomes, recommended workflow, specific asks, rollout plan | Power Point | Beth | 2019-12-31 | ¯ | bar: December 1 to December 5
2. Staff Training and Communication @ All Staff Meetings
a. Module 1:"Why" exercise | 5-min module | SDOH Ambass | 2019-10-31 | ± | bar: October 1 to October 5
b. Module 2: TBD | 5-min module | SDOH Ambass | 2019-11-30 | ± | bar: November 1 to November 19
c. Module 3: TBD | 5-min module | SDOH Ambass | 2019-12-31 | ¯ | bar: December 1 to December 5
3. Staff Training Videos/Emails
a. Elevator speech content/Infographic | email | Beth | 2019-10-07 | ® | bar: October 1
b. PRAPARE Intro/Hearts of Sonoma Data Story- NorCal link, Smart Form | email | Beth | 2019-10-22 | ® | bar: October 3
c. "Why" video- in house | email | Beth | 2019-11-15 | ± | bar: November 2
d. Pilot update, Video: TBD | email | Beth | 2019-11-29 | ± | bar: November 4
e. In house video: Whole Person Care Story | email | Beth | 2019-12-07 | ¯ | bar: December 1
f. Video: PRAPARE Demo? | email | Beth | 2019-12-16 | ¯ | bar: December 3
g. Video: Resources/How to use NorCal Resources | email | Beth | 2019-12-30 | ¯ | bar: December 5
h. Video: How to manage PRAPARE conversation with patients | email | Beth | 2020-01-13 | ¯
4. Other
a. Lo Que Sabes Article | article | Beth | TBD | ¯
b. Posters | posters | Beth | TBD | ¯
c. Email to outside referral orgs | article | Beth | TBD | ¯
|  |  |  | ¯ | September 1: not started
|  |  |  | ± | September 1: in progress
|  |  |  | ® | September 1: complete